## Dev Schedule
Development Plan
Note: This is an estimatation of the time required mostly project is completed before the due date. Only working days are counted.
Important: We ask 20% upfront payment.
Upflence web site | Activity |  |  | Days Required | Total Days | Budgets(k)
| Web | Upfluence Flow | Upfluence Understanding(www.upfluence.com) | 1 | 1 | 1
|  |  | Project Setting | 1 | 2
|  |  | Task Assigning | 1 | 3
|  |  | Feedback | 1 | 4
|  |  | Prepare to start | 1 | 5
|  | Design | Upfluence User Interface(UI) | 20 | 25 | 3
|  |  | UI Approval from the client | 5 | 30
|  | Development | Front-end Development | 20 | 50 | 8
|  |  | Back-end Development | 15 | 65 | 6
|  |  | Front-end/Back-end Intergration | 10 | 75 | 2
|  | Finalizing | Server Management | 3 | 78 | 1
|  |  | Testing | 2 | 80 | 2
|  |  | Final Feedback work | 5 | 85 | 2
[5 empty] | 85 Days | 25 (k)

## Detail
Module | Tasks | Details | Estimates (hrs)
Influencer Features
Service Management. | Table, Actions | Influencer should be able to manage the services it can provide. | 12
Create New Service. | Form | Should be able to create a new service | 10
Orders Management. | Table, Actions | Should be able to manage the orders, pending, inprogress, completed | 16
Withdraw Management. |  |  | 8
Withdraw Money. |  | A portal to make withdrawal of money | 20
Withdrawal History. | Table | History of all withdrawels | 12
Support Ticket Management. | Table | List of all tickets, opened, closed and pending | 16
Open New Ticket. | Form | Form to submit a new ticket | 10
Conversations Management. | Table |  | 40
Profile Setting Management. | Form | Form to update complete profile | 16
2FA Security Management. |  | for singin | 16
SMS & Email Notification & Verification. |  |  | 24
GDPR Policy. |  |  | 6
Livechat, Security Captcha Included. |  | We can decide which service we can you for live chat | 24
Comes with Multi-language Features. | Internalization | functionality to change language | 20
Privacy & TOS. | Static pages |  | 24
User Dashboard Features
Unique Responsive Dashboard. |  | Responsiveness | 20
Deposit Management. |  | Able to deposit money | 26
Deposit History. | Table | History of all deposits | 12
Orders Management. |  | List of created orders | 20
Support Ticket Management. | Table | List of all tickets, opened, closed and pending | 16
Conversations Management. | Table |  | 40
Favorite List Management. | Actions to remove | List of favourite influencers | 18
Reviews Management. |  | Ability to see previous reviews, and to make reviews if pending | 25
Order Reviews. |  | Create a review | 12
Transactions Management. |  |  | 16
Profile Setting Management. |  |  | 16
2FA Security. |  | for signin | 16
SMS & Email Notification & Verification. |  |  | 24
GDPR Policy. |  |  | 6
Livechat, Security Captcha Included. |  |  | 20
Comes with Multi-language Features. | Internalization |  | 20
Privacy & TOS. | Static page |  | 8
Admin Features
Premium Admin Dashboard. |  |  | 24
Manage Clients. |  |  | 30
Manage Influencer. |  |  | 20
Manage Categories. |  |  | 24
Manage Services. |  |  | 30
Manage Orders. |  |  | 20
Manage Hirings. |  |  | 20
Manage Reviews. |  |  | 16
Manage Deposits. |  |  | 18
Manage Withdrawals. |  |  | 18
Manage Support Client. |  |  | 20
Support Influencer. |  |  | 16
Manage Client Report. |  |  | 16
Manage Influencer Report. |  |  | 16
General Setting. |  |  | 30
Manage Language. |  |  | 18
Project management hours |  |  | 100
QA hours |  |  | 200
Additional Features as per (influencity)
General signup as a user
Login to your account
Settings
Profile Edit Section
Password Change
Last login activity logs
Email account Integration
Send and schedule emails from Influencity
Log email exchanges to Influencity automatically
Suggest follow-up tasks and capture contact details from your email
Requires inbox automation
Products & Billing
Subscriptions | FAQ section Subscribe plans
Billing info | logs for billings
Transactions | logs for all transactions
Payment methods | list of cards
Upload your brand logo
Discover Influencers
Search for influencers
select from abailable categories
Filter search | Based on location, gender, age, interest, language, brand affinity, lookalikes, hashtags, keywords on posts, Bio, Ethnicity, account type
Search on network | Instagram, youtube, tiktok
Export search results
Save the search for future 1 click go.
Table of past searches
IRM Overview
Count of influencers added from different social networks.
List creation for IRM overview of influencers only in the list.
Add influencer. | Can add an influencer by adding profile link of social network.
Mark a list or an individual influencer as favourite
Campaigns
Create Campaign
Campaign open view
add influencers in the campaign
Reports
All reports List view
Report open view
adding publications and data for reports creation
Manage publication data
Report settings
Print to PDF
Share
Export report
Delete report
Last but not the least
Data scraping and mining on social platforms